# Project Z: Constraint Math & Feasibility Analysis

Draft v2 (corrected) — February 2026 — Focus: Inpatient Staffing

## 1. Resident Supply (Available Weeks)

Each resident has 48 scheduled weeks/year (8 blocks × 6 weeks). 8 are clinic weeks (the "X"), leaving 40 Y-block weeks. Preliminary interns follow the same rotation schedule as PGY1 but do NOT participate in clinic week (they do something else that week).

|  | Count | Clinic Wks | Y-Block Wks | Total Y-Wks | Notes |
| --- | --- | --- | --- | --- | --- |
| PGY3 | 27 | 8 each | 40 each | 1,080 | Upper level |
| PGY2 | 28 | 8 each | 40 each | 1,120 | Upper level |
| Total Upper Level | 55 | 440 |  | 2,200 | Resident-weeks available |
| PGY1 Categorical | 27 | 8 each | 40 each | 1,080 |  |
| PGY1 Preliminary | 5 | 0 (separate) | 48 each* | 240 | *No clinic week; full 48 wks for rotations |
| Total Interns | 32 |  |  | 1,320 | Intern-weeks available (1,080 + 240) |
| Rotator Intern-Weeks (on floors) |  |  |  | ~180 | Neuro ~103 + Anes ~43 + Psych ~34 |
| GRAND TOTAL SUPPLY |  |  |  |  |  |
| Upper-level resident-weeks |  |  |  | 2,200 |  |
| Intern-weeks (cat + prelim + rotator) |  |  |  | ~1,500 |  |

## 2. Inpatient Demand (Weekly Staffing × 48 Weeks)

| Service | R/week | I/week | R-wks/yr (×48) | I-wks/yr (×48) | Format | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| SLUH Wards | 5 | 10 | 240 | 480 | 3-wk cont. | 5 teams: 1r + 2i |
| (or 6r + 8i variant) | 6 | 8 | 288 | 384 |  | 4 teams 1r+2i, 1 team 2r+0i |
| VA Wards | 5 | 5 | 240 | 240 | 3-wk cont. | 5 teams: 1r + 1i |
| MICU (2 teams) | 4 | 2 | 192 | 96 | 3-wk stag. | PGY3 + PGY2 + intern per team |
| Night Float | 5 | 4 | 240 | 192 | 2-wk cont. | Covers 4r + 3i nightly, built-in days off |
| Diamond | 1 | 0 | 48 | 0 | 1-wk |  |
| Gold | 1 | 0 | 48 | 0 | 1-wk |  |
| Bronze/GI | 1* | 0 | 48 | 0 | Wk on/off | *2 assigned, 1 on at a time |
| Cardiology | 1* | 0-1 | 48 | 0-48 | Wk on/off | *2 assigned, maybe intern |
| ID | 1 | 0 | 48 | 0 | 3-wk cont. | 1 resident, continuous |
| Jeopardy | 1 | 1 | 48 | 48 |  | Backup call |
| TOTAL INPATIENT (standard) | 25 | 22-23 | 1,200 | 1,056-1,104 | per week |  |
| TOTAL INPATIENT (6r SLUH) | 26 | 20-21 | 1,248 | 960-1,008 | per week | Trades 48 R-wks for 96 I-wks |

## 3. Supply vs. Demand: Does It Work?

UPPER LEVEL RESIDENTS (PGY2 + PGY3)

|  | Resident-Wks | Notes |
| --- | --- | --- |
| Supply: Total Y-block weeks | 2,200 | 55 residents × 40 wks |
| Demand: Inpatient (standard SLUH) | (1,200) |  |
| Remaining for Outpatient/Elective | 1,000 |  |
| Per resident per year | ~18.2 wks OP | Out of 40 Y-weeks = 45% OP |
| ACGME: 40 wks outpatient over 3 yrs |  |  |
| OP Y-weeks: ~18.2/yr × 3 = ~55 wks |  |  |
| Plus clinic: 8/yr × 3 = 24 wks |  |  |
| TOTAL OUTPATIENT over 3 yrs | ~79 wks | ✅ Well above 40-wk minimum |
| ACGME: 6 months elective over 3 yrs (~26 wks) |  |  |
| ~55 OP Y-wks over 3 yrs available |  |  |
| Minus required OP rotations = remaining for electives | Likely OK | Depends on required OP rotation count |

INTERNS (PGY1 Categorical + Preliminary + Rotators)

|  | Intern-Wks | Notes |
| --- | --- | --- |
| Supply: Categorical Y-block weeks | 1,080 | 27 interns × 40 wks |
| Supply: Preliminary rotation weeks | 240 | 5 prelims × 48 wks (no clinic week) |
| Supply: Rotator intern-weeks on floors | ~180 | Neuro + Anes + Psych |
| TOTAL INTERN SUPPLY | ~1,500 |  |
| Demand: Inpatient (standard 5r+10i SLUH) | (1,056) |  |
| (or 6r+8i SLUH variant) | (960) | Saves 96 intern-weeks |
| Remaining (standard SLUH) | ~444 |  |
| Remaining (6r+8i variant) | ~540 |  |
| Per categorical intern per year | ~13-17 wks OP | Range depends on SLUH variant + prelim/rotator allocation |

CLINIC WEEK MATH

82 categorical residents (27 PGY3 + 28 PGY2 + 27 PGY1), each doing 8 clinic weeks per year. Prelim interns do NOT do clinic week.

|  | Value | Notes |
| --- | --- | --- |
| Clinic-weeks supplied | 656 | 82 residents × 8 weeks |
| Residents per block (82 ÷ 6) | ~13-14 | Rotating: 14, 14, 14, 13, 14, 13 |
| Clinic-weeks demanded | ~648 | ~13.5/week × 48 weeks |
| Balance | +8 | ✅ Balanced — small surplus |

## 4. Key Findings

| A. | THE MATH WORKS. 55 upper-level residents and 32 interns (plus ~180 rotator weeks) can staff all inpatient services and still have meaningful outpatient/elective time. ACGME minimums appear comfortably achievable. |
| --- | --- |
| B. | CLINIC WEEK IS BALANCED. 82 categorical residents × 8 clinic weeks = 656, yielding ~13-14 in clinic each week. This is close to your target of 15 from the original sheet — you could get to 15 by including some prelims in a modified clinic experience. |
| C. | RESIDENTS HAVE GOOD FLEXIBILITY. ~18 Y-weeks per year for outpatient/elective. Over 3 years = ~55 OP weeks plus 24 clinic weeks = ~79 total outpatient weeks (ACGME needs 40). Elective time (~26 wks needed) should fit comfortably. |
| D. | INTERNS ARE TIGHTER BUT FEASIBLE. ~13-17 OP Y-weeks per year depending on SLUH variant. The 6r+8i SLUH variant gives interns more breathing room (+96 intern-weeks/yr) at modest resident cost (+48 R-wks/yr). |
| E. | NIGHT FLOAT IS THE BIGGEST CONSUMER. 5r + 4i every 2 weeks = 240 R-wks + 192 I-wks per year. That is 20% of resident supply and 18% of categorical intern supply. |
| F. | ROTATORS ARE ESSENTIAL. ~180 intern-weeks from Neuro/Anesthesia/Psych = ~12% of total intern supply. Monthly rotation mismatch with 6-week blocks needs careful boundary management. |
| G. | PRELIMINARY INTERNS ARE A BONUS. 5 prelims × 48 weeks = 240 intern-weeks on the same rotation schedule but without clinic week. This is 16% extra intern capacity above the 27 categoricals. |

## 5. Weekly Snapshot: Where Is Everyone?

| Assignment | Residents | Interns | Subtotal | % of Pool |  |
| --- | --- | --- | --- | --- | --- |
| SLUH Wards | 5 | 10 | 15 | 17% |  |
| VA Wards | 5 | 5 | 10 | 11% |  |
| MICU (2 teams) | 4 | 2 | 6 | 7% |  |
| Night Float | 5 | 4 | 9 | 10% |  |
| Diamond + Gold | 2 | 0 | 2 | 2% |  |
| Bronze + Cards + ID | 3 | 0-1 | 3-4 | 4% |  |
| Jeopardy | 1 | 1 | 2 | 2% |  |
| Inpatient Subtotal | 25 | 22-23 | 47-48 | ~54% |  |
| Clinic Week (categoricals only) | ~8-9 | ~5 | ~13-14 | ~16% |  |
| Prelim (separate activity) |  | ~1 | ~1 | ~1% | In lieu of clinic |
| Outpatient / Elective | ~21-22 | ~5-7 | ~27-28 | ~30% |  |
| GRAND TOTAL | 55 | 32 | 87 | 100% | + rotators |

Note: Rotators add ~4-8 interns on floors at any given time (varies by month), supplementing the numbers above.

## 6. Open Questions Before Building Full Schedule

| 1. | DAYS OFF MECHANICS: 10 days per 6-wk block — are these within rotations (weekends off, golden weekends) or explicitly scheduled non-working days that reduce weekly coverage? |
| --- | --- |
| 2. | PRELIM DURING CLINIC WEEK: What do prelims do during the week when categoricals are in clinic? If they can backfill a ward slot, that helps coverage. |
| 3. | NON-BLOCK WEEKS (4 per year): What staffing looks like during holidays and transitions? Skeleton crew on wards + NF only? |
| 4. | MICU PGY SPLIT: 2 teams × 3-wk staggered = 32 PGY3-weeks + 32 PGY2-weeks in MICU/yr. Each PGY3 averages ~3.6 wks/yr in MICU. Is that right amount? |
| 5. | ROTATOR BOUNDARY MANAGEMENT: Rotators switch monthly; your blocks are 6 weeks. How do you want to handle the mismatch? (e.g., rotator always takes intern slot 1 on a given team) |